## Slide 1: Project Status Report: Artemis
Executive Summary | This report demonstrates the completed and upcoming milestones, the accomplishments we recently did, the risks, issues and dependencies that we are and will face, and the upcoming steps we are planning to do.
Recent Accomplishments
Finishing Demo 1 Continued discussing reworks for Demo 2 Implemented feedback from clients Brought RTM up to date
Next Steps
Finish and Present Demo 2 Work on updates of documentation Implement feedback from Demo 2 for final demonstration.
Milestones |  |  | 
Milestone | Baseline | Expected | RAG
Demo 1 presentation / 50% complete | 2/12 | EOD 3/05 | C
Update RTM | 3/20 | EOD 4/01 | C
Demo 2 presentation / 75% complete | 3/20 | EOD 4/01 | G
Final Documentation ( RTM, PMP, Progress Report) | 3/20 | EOD 4/16 | G
Final Demo 3 presentation / 100% complete | 3/20 | EOD 4/16 | G
Risks, Issues, and Dependencies
Dependencies on Google Calendar booking Issues with integration via Fusion since its closed source
Status Key: | Green: On Target | Amber: Risks to Timeline, Scope, or Budget | Red: Requires Corrective Action | Complete: Work Complete
Status Date | 04/01/2024
Execution Owner | The Kid's Center for Pediatric Therapies
Project ID | Artemis
RAG Status | On Target
Notes: Need a high-level dashboard for operational leaders. Must tell the whole story (single source of truth for staffing, outreach, engagement, etc.).
Focus on CM and DM first. We don’t have good contact information for members. Bi-weekly update meeting.